## Sheet1
Task | 1/13-1/19 | 1/20-1/26 | 1/27-2/2 | 2/3-2/9 | 2/10-2/16 | 2/16-2/23 | 2/24-3/2 | 3/3-3/9 | 3/10-3/16 | 3/17-3/23 | 3/24-3/30 | 3/31-4/6 | 4/7-4/13
Image attack subsystem functional
Pod attack subsystem functional | [10 empty] | Not Started
Cluster attack subsystem functional | [10 empty] | In Progress
Implement cluster data reading (KubeShark) | [10 empty] | Completed
Implement data interactions within cluster | [10 empty] | Behind Schedule
Status Update #2 (2/5)
GUI can interface with cluster
GUI can run attacks
Status Update #3 (2/19)
Make attacks executable scripts in python
Attack data can be gathered
Status Update #4 (3/5)
Make GUI fucntion properly (buttons actually run attacks) | [8 empty] | Spring Break
GUI displays relevant data for each attack type
Status Update #5 (3/26
Debugging
FInal Design Presentation (4/9)